## Phase 1
Sr No | Feature | User end | Delivery
1 | Company User login | Company Admin
2 | Super admin create questions | Super admin
3 | Invite to first interview | Company Admin
4 | Access test and start test without timer and browser back handling | Candidate | 2018-02-09
5 | Timer logic + browser back and close handling | Candidate
6 | Expire security token after 6 days logic | Candidate | 2018-02-19
7 | View test results | Company Admin
8 | Invite to second round | Company Admin
9 | Candidate second round test page | Candidate
10 | Candidate second round submission page logic | Candidate | 2018-03-02
11 | Shortlisted candidates | Company Admin
12 | Email template management | Company Admin | 2018-03-08
13 | Manage/view tests created while sending an invite to any candidate | Company Admin
14 | Manage companies | Super admin
15 | Manage company users | Super admin | 2018-03-15
16 | Login with feature: to allow login with any company user | Super admin | 2018-03-23